## 2026_01
Project_ID | Project_Name | Portfolio_ID | PM | Planned_Budget | Actual_Budget | Planned_Progress (%) | Actual_Progress (%)
P1 | Billing | PF1 | Nikola | 100000 | 95000 | 30 | 25
P2 | AI Engine | PF1 | Elena | 200000 | 210000 | 40 | 35
P3 | Mobile App | PF2 | Stefan | 150000 | 140000 | 50 | 55

## 2026_02
Project_ID | Project_Name | Portfolio_ID | PM | Planned_Budget | Actual_Budget | Planned_Progress (%) | Actual_Progress (%)
P1 | Billing | PF1 | Nikola | 100000 | 110000 | 60 | 55
P2 | AI Engine | PF1 | Elena | 200000 | 230000 | 70 | 60
P3 | Mobile App | PF2 | Stefan | 150000 | 155000 | 80 | 75

## 2026_03
Project_ID | Project_Name | Portfolio_ID | PM | Planned_Budget | Actual_Budget | Planned_Progress (%) | Actual_Progress (%)
P1 | Billing | PF1 | Nikola | 100000 | 120000 | 100 | 90
P2 | AI Engine | PF1 | Elena | 200000 | 250000 | 100 | 85
P3 | Mobile App | PF2 | Stefan | 150000 | 160000 | 100 | 100

## 2026_04
Project_ID | Project_Name | Portfolio_ID | PM | Planned_Budget | Actual_Budget | Planned_Progress (%) | Actual_Progress (%)
P1 | Billing | PF1 | Nikola | 100000 | 100000 | 100 | 100
P2 | AI Engine | PF1 | Elena | 200000 | 220000 | 100 | 95
P4 | New App | PF2 | Stefan | 150000 | 160000 | 100 | 45

## portfolio
Portfolio_ID | Portfolio_Name | Director | Strategic_Goal | Total_Budget
PF1 | Digital Transformation | Marin | Modernize core systems | 500000
PF2 | Customer Experience | Ivana | Improve mobile and UX | 300000